## Sheet1
ID | Owner | Type | As a/an… | I want to… | So that… | Expected hour to complete | Notes | Priority | Status
1 | shiqiw | Feature | User(both instructor and student) | Be able to register and login to my account | I can use all the features provided in Cognita | 1hr |  | High | To do
2 | shiqiw | Feature | student who has not registered for the course when looking at the course's detail page | Be able to see the course introduction and overview of content | I can decide whether to take the course or not | 2.5hr |  | Medium | To do
3 | shiqiw | Feature | student who has not registered for the course when looking at the course's detail page | Be able to click some button to register for this course | I can get full access to the course content and start learning | 1hr | This feature should be implemented with Ajax, so that the page will not be refreshed when the user click 'register' | Medium | To do
4 | shiqiw | Feature | student who has registered for the course | Be able to see the readings in each lecture without leaving the course page | I can mark it as completed when I'm done reading the material | 2hr | This feature should be implemented with Ajax, the actual content is loaded after rendering the page. Primary supported file type: .pdf | Medium | To do
5 | shiqiw | Feature | student who has registered for the course | Be able to see the video in each lecture without leaving the course page | I can mark it as completed when I'm done watching the video | 1hr | This feature should be implemented with Ajax, the actual content is loaded after rendering the page. Supported video source: YouTube | Medium | To do
6 | shiqiw | Feature | student who has registered for the course | Be able to see the link to take the quizzes and tests | I can go to the quiz/test taking page and do the quiz/test | 0.5hr |  | Medium | To do
7 | shiqiw | Knowledge acquisition | student who has registered for the course | Be able to see the readings in .md and .tex format in each lecture without leaving the course page | I can mark it as completed when I'm done reading the material | ~7hr | Implement this feature only if have extra time in sprint 1 | Low | To do
8 | shiqiw | Feature | student who has registered for the course, and has finished with a reading or a video | Be able to mark it as completed/uncompleted | I can record my progress | 2hr | This feature should be implemented with Ajax, so that the page will not be refreshed when the user click 'completed/umcompleted' | Medium | To do