## Sheet1
Sprint Owner | mohanf
ID | Owner | Type | As a/an… | I want to… | So that… | Expected hour to complete | Notes | Priority
1 | shiqiw | Feature | student | be able to take notes when I'm reading the materials or watching the videos | I can note done what I want to note done | 6hr |  | Medium
2 | shiqiw | Feature | student | have my notes automatically saved | I don't have to manually save it every time I make any modification | 5hr |  | Medium
3 | shiqiw | Feature | user | have a home page which displays hot courses | I can see what courses this website has | 4hr |  | Medium
4 | shiqiw | Feature | user | Have more information on my profile page | I can have a clear idea of my status | 2hr |  | Medium
5 | shiqiw | Feature | student | see the profile page of the course instructor | I can know more about the instructor | 2hr |  | Medium
6 | mohanf | Preparation | application developer | Download jQuery UI and learn to use jQuery UI sortable plugin | add reordering function in course creation page | 2hr |  | High
7 | mohanf | Feature | instrctor(course creator) | Reorder parts in a single lecture | the user can use mouse to drag and click to change the order of the materials they created | 3hr | This will be realized by ajax | High
8 | mohanf | Feature | instrctor(course creator) | Reorder modules in a single course | the user can use mouse to drag and click to change the order of the lectures and tests they created | 3hr | This will be realized by ajax | High
9 | mohanf | Preparation | application developer | Download django-CKEditor and learn to use including upload image | add function of a rich text format editor | 3hr |  | Medium
10 | mohanf | Feature | instrctor(course creator) | create their reading materials with format and images possibly | the type of reading matrials and the flexibility of user mateiral is largely increased | 4hr |  | Medium
11 | mohanf | Feature | user | search for the course they need | search in the search box to find the target course | 1hr |  | Medium
12 | mohanf | feature | user | sort the search result | they can change the order of displaying search result of either creating time or popularity | 1hr |  | Low
13 | mohanf | feature | user | filter the search result | they can choose to filter by various numbers of categories of course | 3hr |  | Low
14 | mohanf | front end | application developer | improve the user interface | user can feel better and more convinient when using it | 4hr |  | Low
15 | xinyangg | Feature | student | be able to take quiz | I can evaluate my performance on a specific lecture | 5hr |  | High
16 | xinyangg | Feature | student | be able to take test | I can evaluate my performance on a specific course | 5hr |  | High
17 | xinyangg | Feature | student | be able to get my grade after taking quiz or test | I can get a general evaluation of my quiz or test | 5hr |  | High
18 | xinyangg | Feature | student | be able to get correct answer after taking quiz or test | I can get a feedback after a quiz or test | 6hr |  | Medium
19 | xinyangg | Feature | instrctor(course creator) | be able to reorder the questions I have created | I can get modify the order of questions after created | 6hr |  | Low